## 🗺 Overview
VIVIM — Production Beta Workplan
Dependency-ordered atomic task plan · March 2026 · Target: Production-ready beta
Phase | Name | Objective | Tasks | Est. Days | Team | Status
P0 | Security Hardening | Fix auth gaps, remove dev bypasses, harden all unprotected routes, rate-limit everything, secrets rotation | 14 | 3-5 d | Backend | 🔴 BLOCKING
P1 | Capture Reliability | Fix ownerId assignment, add retry/circuit-breaker, validate all 9 extractors, provider health monitoring | 18 | 5-7 d | Backend | 🔴 BLOCKING
P2 | Core UX Polish | Onboarding flow, mobile PWA, error states, loading skeletons, offline indicators, PWA manifest | 22 | 7-10 d | Frontend | 🟠 HIGH
P3 | Trust & Data Integrity | At-rest encryption for memories/messages, per-user data isolation path, GDPR deletion compliance | 20 | 6-9 d | Full-stack | 🟠 HIGH
P4 | Social & Discovery | Feed algorithm, sharing discovery, public ACU search, moderation enforcement, notification system | 24 | 8-12 d | Full-stack | 🟡 MEDIUM
P5 | Scale & Infrastructure | CI/CD pipeline, DB backups, CDN, health checks, monitoring/alerting, load testing, P2P bootstrap | 18 | 5-8 d | DevOps | 🟡 MEDIUM
⚠ CRITICAL PATH — Must complete P0 → P1 before any user-facing beta. P2+P3 can run in parallel. P4 requires P1+P2. P5 runs alongside all phases.
KEY FINDINGS FROM AUDIT
| ✅ STRONG | Feature completeness is very high — 22/28 features at 100%. Most of the hard product work is done.
| ✅ STRONG | All 9 provider extractors implemented. ACU pipeline, context engine, sharing, social all functional.
| ✅ STRONG | Async jobs have error handling and retry logic. Background workers configured and operational.
| 🔴 CRITICAL | POST /api/v1/capture/capture assigns API key auth only — no ownerId/userId attached. Data orphaned.
| 🔴 CRITICAL | Multiple /api/v2/context/* routes have no auth middleware — any user can read any context.
| 🔴 CRITICAL | All /api/v1/acus/* routes are public (auth: None). ACU data fully exposed.
| 🔴 CRITICAL | SKIP_AUTH_FOR_DEVELOPMENT env var exists — must be confirmed disabled in prod.
| 🔴 CRITICAL | ZAI_API_KEY has a default hardcoded development key in .env.example — must rotate.
| 🟠 HIGH | Memories, Messages, User settings stored as PLAINTEXT at rest. No at-rest encryption.
| 🟠 HIGH | No CSRF protection. Relies solely on CORS — insufficient for a social platform.
| 🟠 HIGH | JWT expiration not set in code (session-based only) — tokens may never expire.
| 🟠 HIGH | No dead letter queue — failed jobs are silently dropped after 3 retries.
| 🟠 HIGH | P2P_BOOTSTRAP_PEERS is empty — P2P networking configured but non-operational.
| 🟡 MEDIUM | User.settings JSON field queried frequently — should be normalized to dedicated columns.
| 🟡 MEDIUM | Missing composite index [userId, type, importance] on Memory table — will degrade at scale.
| 🟡 MEDIUM | No CDN, no DB backup strategy, no health check endpoints documented for prod.

## P0 · Security
P0 · Security Hardening
# | Task ID | Area | Task Title | What To Do | File(s) / Location | Depends On | Effort (hrs) | Priority | Status | Acceptance Criteria
1 | P0-01 | Auth | Remove SKIP_AUTH_FOR_DEVELOPMENT | Audit all code paths that read SKIP_AUTH_FOR_DEVELOPMENT. Remove the flag and its branches entirely. Add a CI check that fails if the string is found in source. | server/src/middleware/auth.js, server/.env.example | — | 2 | BLOCKING | TODO | Flag does not exist in codebase. CI lint rule added. Build fails if reintroduced.
2 | P0-02 | Auth | Add auth middleware to all ACU routes | Every /api/v1/acus/* route currently has auth: None. Add requireAuth or authenticateDID to all write routes. Make read routes optionalAuth with owner-scoped filtering. | server/src/routes/acus.js | — | 3 | BLOCKING | TODO | GET /acus/:id returns 401 for private ACUs without auth. Write routes 401 unauthenticated.
3 | P0-03 | Auth | Add auth to /api/v2/context/* routes | All context routes currently have auth: None. Wrap with authenticateDID. Ensure every query is scoped to req.userId. | server/src/routes/context-v2.js | — | 3 | BLOCKING | TODO | GET /context/bundles without token returns 401. User A cannot see User B's bundles.
4 | P0-04 | Capture | Assign ownerId/userId during capture | POST /capture/capture currently sets no ownerId on created Conversation records. Extract userId from API key or session and assign to Conversation.ownerId and all child ACUs. | server/src/routes/capture.js, server/src/services/storage-adapter.js | P0-02 | 4 | BLOCKING | TODO | After capture, Conversation.ownerId === authenticated user's id. ACUs have correct authorDid.
5 | P0-05 | Secrets | Rotate all default/hardcoded secrets | Replace ZAI_API_KEY default in .env.example with placeholder. Audit all .env.example files across monorepo for real values. Add git-secrets or truffleHog to pre-commit hook. | server/.env.example, all workspace .env files | — | 2 | BLOCKING | TODO | No real secrets in any committed file. Pre-commit hook blocks future commits with secrets.
6 | P0-06 | Auth | Set JWT expiration + refresh flow | jsonwebtoken sign calls must include expiresIn (recommend 15m access, 7d refresh). Implement POST /api/v1/auth/refresh endpoint. Update frontend to handle 401 → refresh → retry. | server/src/middleware/auth.js, server/src/routes/auth.js, pwa/src/ | — | 5 | HIGH | TODO | Access token expires in 15 min. Refresh endpoint issues new token. Frontend handles silently.
7 | P0-07 | Security | Implement CSRF protection | Add csurf or use double-submit cookie pattern. Apply to all state-mutating routes (POST/PUT/DELETE). Update frontend to include CSRF token in headers. | server/src/server.js (middleware setup), pwa/ (fetch wrapper) | P0-06 | 4 | HIGH | TODO | POST without CSRF token returns 403. Automated test confirms protection.
8 | P0-08 | Security | Add rate limiting to all endpoints | RATE_LIMIT_MAX is configured but coverage may be incomplete. Audit every router file. Apply express-rate-limit with appropriate limits per domain (auth: 5/min, capture: 10/min, API: 100/min). | server/src/server.js, all router files | — | 3 | HIGH | TODO | Sending 200 rapid requests to /api/v1/auth returns 429 after threshold. Verified for 3+ domains.
9 | P0-09 | Auth | Enforce ownership checks in all service layers | Audit every Prisma query in services. Any findUnique/findFirst that could return another user's data must add where: { userId: req.userId }. Write a query review checklist. | server/src/services/*, server/src/routes/* | P0-03 | 6 | HIGH | TODO | User A authenticated request cannot retrieve User B's conversations, memories, or bundles. Add integration tests.
10 | P0-10 | Security | Audit and harden CORS configuration | CORS_ORIGINS currently set to openscroll.com domains (not vivim.app). Update to correct production domains. Ensure no wildcard. Add CORS tests. | server/.env.example, server/src/server.js | — | 2 | HIGH | TODO | Requests from unauthorized origin return CORS error. Verified in browser and automated test.
11 | P0-11 | Auth | Remove or gate debug endpoints | DEBUG=true enables debug endpoints. Ensure these are only accessible in dev. Add NODE_ENV check so they 404 in production. | server/src/server.js, any /debug/* routes | P0-01 | 2 | HIGH | TODO | All debug routes return 404 when NODE_ENV=production.
12 | P0-12 | Security | Encrypt mfaSecret at rest | mfaSecret is currently stored but encryption path is unclear. Implement AES-GCM encryption/decryption using server-side key before write, after read. | server/src/services/mfa-service.js, server/src/lib/crypto.js | — | 3 | HIGH | TODO | mfaSecret column in DB is never plaintext. Verified via DB inspection.
13 | P0-13 | Admin | Harden admin panel authentication | Admin auth uses role OR IP allowlist. Verify role-based check is correctly implemented. Add 2FA requirement for admin users. Audit admin-auth.js logic. | server/src/middleware/admin-auth.js | P0-12 | 3 | HIGH | TODO | Admin panel requires valid admin role + active 2FA. IP allowlist as secondary defense only.
14 | P0-14 | Security | Add security headers middleware | Add helmet.js to set Content-Security-Policy, X-Frame-Options, X-Content-Type-Options, Referrer-Policy, HSTS headers. | server/src/server.js | — | 2 | MEDIUM | TODO | curl -I on any endpoint shows all security headers. CSP does not break PWA.

## P1 · Capture
P1 · Capture Reliability
# | Task ID | Area | Task Title | What To Do | File(s) / Location | Depends On | Effort (hrs) | Priority | Status | Acceptance Criteria
1 | P1-01 | Capture | Validate ownerId flows end-to-end | After P0-04, write integration test that captures a conversation and asserts Conversation.ownerId, all ACU.authorDid, all Memory.userId are set to the authenticated user. Fail build if any are null. | server/tests/capture.test.js (new) | P0-04 | 4 | BLOCKING | TODO | Test suite passes. Null ownerId after capture is a build failure.
2 | P1-02 | Capture | Implement circuit breaker for provider extractors | Wrap each provider extractor call with opossum circuit breaker. If a provider fails 3 consecutive times, open the circuit for 5 minutes. Log circuit state. Expose /api/admin/capture/health endpoint. | server/src/services/extractor.js, server/src/routes/admin/ | P0-09 | 6 | BLOCKING | TODO | Simulating ChatGPT extractor failure opens circuit. Admin endpoint shows provider health states.
3 | P1-03 | Capture | Add dead letter queue for failed captures | Current retry logic drops after 3 attempts. Create a failed_captures table or Redis list. Store failed capture attempts with error detail, provider, userId, url. Add admin UI to retry or dismiss. | server/src/services/queue-service.js, schema.prisma (new model), server/src/routes/admin/ | P1-02 | 8 | HIGH | TODO | Failed capture after 3 retries appears in failed_captures. Admin can view and retry.
4 | P1-04 | Capture | Test all 9 extractors against live providers | Run each extractor against a real conversation URL for each provider. Document pass/fail. Fix any that are broken. Create regression test fixture set with stored HTML snapshots. | server/src/extractors/*, server/tests/extractors/ | P1-01 | 10 | HIGH | TODO | All 9 providers extract title, messages, metadata correctly. Regression tests pass in CI.
5 | P1-05 | Capture | Add provider health monitoring + alerting | Create a background job that pings each provider with a known URL every 15 minutes. Record success/failure. Dashboard shows provider uptime. Alert when provider fails >50% for 30 min. | server/src/services/ (new: provider-health-monitor.ts), server/src/routes/admin/ | P1-02 | 6 | HIGH | TODO | Admin panel shows per-provider health over 24h. Alert fires when provider is down.
6 | P1-06 | Capture | Implement exponential backoff on extractor retries | Current retry is fixed. Change to exponential backoff: 1s, 5s, 30s. Add jitter. Log retry attempts with error context. | server/src/services/queue-service.js, server/src/services/extractor.js | — | 3 | HIGH | TODO | Retry delays are measurably 1s, 5s, 30s ±jitter. Verified in logs.
7 | P1-07 | Capture | Handle CAPTCHA/challenge page detection | When Playwright encounters a CAPTCHA or challenge page, detect it via DOM pattern matching. Return a structured error (CAPTCHA_REQUIRED) instead of crashing. Return user-friendly message in API response. | server/src/services/extractor.js, server/src/extractors/base-extractor.js (new) | P1-04 | 5 | HIGH | TODO | Capture returns {error: 'CAPTCHA_REQUIRED', provider: 'chatgpt'} when challenged. Frontend shows actionable message.
8 | P1-08 | Capture | Add session expiration detection and refresh | If extraction fails due to expired session (login redirect detected), return SESSION_EXPIRED error. Frontend prompts user to re-authenticate with provider. | server/src/extractors/*, pwa/src/pages/Capture.tsx | P1-07 | 4 | MEDIUM | TODO | Session expiry during extraction returns SESSION_EXPIRED. UI shows clear recovery path.
9 | P1-09 | ACU | Add ACU blockchain verification (complete 75→100%) | ACU signing is 75% complete — blockchain verification is not implemented. Define what 'verification' means (local Ed25519 verify vs on-chain). Implement local verification on read. Document the verification flow. | server/src/lib/crypto.js, server/src/routes/acus.js | P0-02 | 6 | MEDIUM | TODO | GET /acus/:id response includes verified: true/false. Ed25519 signature verified on read.
10 | P1-10 | Memory | Add manual memory extraction trigger to UI | Memory extraction is 75% complete — ad-hoc triggering needs work. Add 'Extract Memories' button to ConversationView. Wire to POST /memory endpoint. Show extraction status. | pwa/src/pages/ConversationView.tsx, server/src/workers/memory-worker.js | P0-09 | 4 | MEDIUM | TODO | User can trigger memory extraction from UI. Status shown. Memories appear in memory list after.
11 | P1-11 | Infra | Add job monitoring dashboard to admin | No job monitoring dashboard exists. Add a page to AdminPanel showing: all active jobs, last run time, success/failure count, dead letter queue size. Use polling or Socket.IO. | pwa/src/pages/AdminPanel.tsx, server/src/routes/admin/ | P1-03 | 5 | MEDIUM | TODO | Admin panel shows live job status. DLQ items visible and actionable.
12 | P1-12 | Capture | Rate-limit batch capture endpoint | POST /capture/capture/bulk has no rate limiting — could overwhelm Playwright pool. Add per-user rate limit (e.g. 20 captures/hour). Queue excess requests. | server/src/routes/capture.js | P0-08 | 3 | MEDIUM | TODO | Bulk capture beyond limit returns 429 with Retry-After header.
13 | P1-13 | Infra | Configure Playwright browser pool | PLAYWRIGHT_BROWSER_PATH not configured for prod. Set up persistent browser pool (e.g. 3 instances). Document browser installation in deployment runbook. | server/.env.example, server/src/services/extractor.js, deployment docs | — | 4 | HIGH | TODO | 3 browser instances pre-warmed on server startup. Capture latency <5s for simple conversations.
14 | P1-14 | Capture | Add capture progress streaming to frontend | Capture currently shows no progress. Use Socket.IO to stream capture progress events (detecting, extracting, generating ACUs, done). Display progress bar in Capture.tsx. | server/src/routes/capture.js, pwa/src/pages/Capture.tsx, pwa/src/components/GlobalSocketListener.tsx | P1-13 | 5 | MEDIUM | TODO | Capture UI shows real-time progress. User knows when ACUs are ready.
15 | P1-15 | Capture | Write capture integration test suite | Create comprehensive test suite: unit tests for each extractor, integration tests for full pipeline, load test with 10 concurrent captures. Run in CI. | server/tests/capture/*, .github/workflows/ | P1-04, P1-13 | 8 | HIGH | TODO | CI runs capture tests on every PR. Tests cover all 9 providers with HTML fixtures.
16 | P1-16 | Capture | Document capture API for browser extension | Swagger docs exist (ENABLE_SWAGGER=true). Ensure all capture routes are fully documented with request/response examples. This unblocks future browser extension development. | server/src/routes/capture.js (JSDoc/Swagger annotations) | P1-15 | 3 | LOW | TODO | Swagger UI shows all capture endpoints with working Try-It-Out examples.
17 | P1-17 | Capture | Add Sentry error tracking to capture pipeline | SENTRY_DSN is optional in .env. Configure Sentry for production. Add meaningful context (provider, userId, url) to capture error events. | server/src/server.js, server/src/services/extractor.js | — | 3 | HIGH | TODO | Failed captures appear in Sentry with provider, userId, error type. Alerts configured.
18 | P1-18 | Capture | Provider extraction fallback strategy | When primary Playwright extraction fails, attempt HTML-only extraction via Cheerio as fallback. Capture partial data rather than returning error. Mark conversation as partially_captured. | server/src/services/extractor.js, server/src/extractors/ | P1-07 | 6 | MEDIUM | TODO | ChatGPT conversation with blocked Playwright still returns partial data via Cheerio fallback.

## P2 · UX Polish
P2 · Core UX Polish
# | Task ID | Area | Task Title | What To Do | File(s) / Location | Depends On | Effort (hrs) | Priority | Status | Acceptance Criteria
1 | P2-01 | Onboarding | Build guided first-run onboarding flow | New user currently lands without guidance. Create OnboardingFlow component: Step 1 (welcome + identity confirm), Step 2 (import first conversation with guided helper), Step 3 (context engine intro), Step 4 (done). Store completion in localStorage/user settings. | pwa/src/pages/ (new: Onboarding.tsx), pwa/src/components/onboarding/ | P0-06 | 10 | HIGH | TODO | New user sees onboarding. Skippable. Completion tracked. Not shown again after done.
2 | P2-02 | Onboarding | Add sample/demo conversation for new users | New users have nothing in their feed. Seed a demo conversation on first login. Add 'Load Demo Data' button on empty state. Demo data is clearly labelled. | server/prisma/seed-real-data.ts, pwa/src/pages/Home.tsx | P0-04 | 4 | HIGH | TODO | First-time user sees demo conversation. Empty state has helpful action, not blank screen.
3 | P2-03 | Mobile | Audit and fix PWA manifest + installability | Verify manifest.json has correct icons (192px, 512px maskable), start_url, display:standalone, theme_color. Test Add to Home Screen on iOS Safari and Android Chrome. Fix any install prompts. | pwa/public/manifest.json, pwa/index.html | — | 4 | HIGH | TODO | Lighthouse PWA score ≥90. App installable on iOS + Android. Splash screen correct.
4 | P2-04 | Mobile | Mobile layout audit and responsive fixes | Test every page on 390px width (iPhone 15) and 414px (iPhone Plus). Fix overflow, tap targets <44px, modals, and navigation. Priority pages: Home, Capture, ConversationView, Settings. | pwa/src/pages/*, pwa/src/components/* | — | 8 | HIGH | TODO | All priority pages usable on 390px. No horizontal scroll. All tap targets ≥44px.
5 | P2-05 | UX | Add loading skeletons to all data-fetching views | Pages that fetch data (Home, ConversationView, Analytics) should show skeleton placeholders instead of spinners or blank screens during load. Use Tailwind animate-pulse pattern. | pwa/src/pages/Home.tsx, pwa/src/pages/ConversationView.tsx, pwa/src/pages/Analytics.tsx | — | 6 | HIGH | TODO | Loading state for each page shows content-shaped skeletons. No blank flash on load.
6 | P2-06 | UX | Design and implement comprehensive error states | Network errors, API failures, empty states — all need designed states. Create ErrorState, EmptyState, NetworkError components. Apply to all pages. No raw 'Something went wrong' strings. | pwa/src/components/ (new: ErrorState.tsx, EmptyState.tsx), all pages | — | 6 | HIGH | TODO | Every page handles error + empty state gracefully. Error messages are human-readable and actionable.
7 | P2-07 | UX | Add offline indicator and offline mode UX | Dexie/IndexedDB is implemented but offline UX is unclear. Add offline banner when network is down. Show which features work offline. Queue captures for retry when online. | pwa/src/components/ (new: OfflineBanner.tsx), pwa/src/stores/sync.store.ts | P2-06 | 5 | MEDIUM | TODO | Going offline shows banner. Capture attempt queues rather than errors. Sync on reconnect.
8 | P2-08 | UX | Simplify context engine terminology and UX | 'ContextCockpit', 'ACU', 'remux', 'bundle' are opaque to new users. Create a simplified view with friendly labels. Show context as 'Your AI Memory' not 'Context Engine'. Advanced mode still accessible. | pwa/src/pages/ContextCockpitPage.tsx, pwa/src/components/ContextCockpit.tsx | P2-01 | 6 | HIGH | TODO | New user can understand what context engine does in <30 seconds. Power user can access full view.
9 | P2-09 | UX | Add notification system (in-app) | Users have no way to know when: share is accepted, friend request received, extraction complete. Add in-app notification bell with unread count. Persist notifications in DB. | pwa/src/components/ (new: NotificationBell.tsx), server/src/routes/ (new: notifications.js), schema.prisma (Notification model) | P0-09 | 10 | HIGH | TODO | User receives in-app notification for: capture complete, share accepted, friend request. Badge count accurate.
10 | P2-10 | UX | Improve share/receive flow UX | Share creation and receiving (Share.tsx, Receive.tsx) work but may lack polish. Add: share preview before sending, clear permission summary on receive, copy-to-clipboard for share links, QR code generation. | pwa/src/pages/Share.tsx, pwa/src/pages/Receive.tsx | P0-09 | 5 | MEDIUM | TODO | Share flow: user sees preview, copies link in 1 click. Receive flow: permissions clearly shown before accept.
11 | P2-11 | UX | Add search improvements (filters, facets) | Search.tsx exists. Add filters: by provider, date range, tag, conversation type. Add search facets in results. Search should cover ACUs and memories, not just conversations. | pwa/src/pages/Search.tsx, server/src/routes/conversations.js | — | 6 | MEDIUM | TODO | Search results filterable by provider and date. ACUs appear in results alongside conversations.
12 | P2-12 | UX | Build settings page completeness pass | Settings.tsx exists but may not expose all configurable options. Audit: provider connections (BYOK), context engine sliders, notification prefs, privacy settings, account danger zone (delete/export). Make all settings discoverable. | pwa/src/pages/Settings.tsx, pwa/src/pages/Account.tsx | P0-06 | 6 | MEDIUM | TODO | All documented settings accessible from Settings page. Nothing buried in other pages only.
13 | P2-13 | UX | Add conversation tagging and organization UI | tags field exists on Conversation model. Add tag creation, editing, and filtering in the Home feed. Add bulk tag operations. Show tag chips on conversation cards. | pwa/src/pages/Home.tsx, pwa/src/components/ (new: TagEditor.tsx) | — | 5 | MEDIUM | TODO | User can add/remove tags on conversations. Feed filterable by tag.
14 | P2-14 | Mobile | Implement app-to-app share target (Web Share Target API) | Register the PWA as a share target so users can share conversation URLs from mobile browser directly to VIVIM for capture. | pwa/public/manifest.json, pwa/src/pages/CaptureSimple.tsx | P2-03 | 4 | MEDIUM | TODO | On Android, sharing a URL from Chrome browser shows VIVIM as a share target. URL passed to capture.
15 | P2-15 | Perf | Lighthouse performance audit and fixes | Run Lighthouse on Home, ConversationView, Capture. Target: Performance ≥85, Accessibility ≥90. Fix top 5 issues per page. Add Lighthouse to CI via lhci. | pwa/ (across pages and components) | P2-04, P2-05 | 8 | MEDIUM | TODO | Lighthouse scores: Performance ≥85, Accessibility ≥90, Best Practices ≥90, PWA ≥90.
16 | P2-16 | UX | Add conversation import history and status page | Users have no way to see past capture attempts, their status, or errors. Create an Import History page showing: URL, provider, status, time, error (if any), retry button. | pwa/src/pages/ (new: ImportHistory.tsx), server/src/routes/capture.js | P1-03 | 5 | MEDIUM | TODO | User can see all past captures with status. Can retry failed ones from UI.
17 | P2-17 | UX | Keyboard shortcuts and accessibility audit | Add keyboard shortcuts for power users: ⌘K for search, ⌘N for new chat, ⌘I for import. Run axe accessibility audit. Fix critical and serious issues. | pwa/src/components/ (new: KeyboardShortcuts.tsx), all pages | P2-15 | 6 | LOW | TODO | Core shortcuts documented and functional. axe reports zero critical accessibility violations.
18 | P2-18 | Perf | Implement PWA background sync for captures | Register a Background Sync service worker event. Queue failed captures in IndexedDB. Retry automatically when connectivity restored. Show sync status in UI. | pwa/public/sw.js (or vite-pwa config), pwa/src/stores/sync.store.ts | P2-07 | 6 | LOW | TODO | Capture attempted offline queues. On reconnect, auto-retries without user action.
19 | P2-19 | UX | Add 'what's new' changelog / feature announcements | Users won't know when new features ship. Add a simple in-app changelog modal triggered on first load after a new version. Store version in localStorage. Copy-driven, not technical. | pwa/src/components/ (new: WhatsNew.tsx) | P2-01 | 3 | LOW | TODO | New version triggers modal with feature highlights. Dismissable. Only shown once per version.
20 | P2-20 | UX | Dark mode / theme support | TailwindCSS 4 has dark mode support. Audit all components for dark mode compatibility. Add theme toggle (light/dark/system). Persist preference. | pwa/src/*, pwa/tailwind.config.* | P2-15 | 6 | LOW | TODO | Dark mode toggle works. All pages render correctly in dark mode. Preference persisted.
21 | P2-21 | UX | ACU viewer polish and rich content rendering | ACUViewer.tsx exists. Ensure it renders: code blocks with syntax highlighting (Shiki), math (KaTeX), tables, images, and markdown correctly. Add copy button for code blocks. | pwa/src/components/ACUViewer.tsx | — | 4 | MEDIUM | TODO | ACUs with code, math, and tables render correctly. Code blocks have copy button. No raw markdown shown.
22 | P2-22 | UX | Implement fork/remux UX flow end-to-end | ForkButton and RemuxDialog exist. Test full flow: click fork → dialog → configure → create → navigate to forked ACU. Fix any broken steps. Add fork lineage visualization. | pwa/src/components/ForkButton.tsx, pwa/src/components/RemuxDialog.tsx, pwa/src/components/ACUGraph.tsx | P0-02 | 5 | MEDIUM | TODO | Fork flow works end-to-end in 3 clicks. New ACU shows parent lineage. ACUGraph renders ancestry.

## P3 · Trust & Data
P3 · Trust & Data Integrity
# | Task ID | Area | Task Title | What To Do | File(s) / Location | Depends On | Effort (hrs) | Priority | Status | Acceptance Criteria
1 | P3-01 | Encryption | Encrypt memories at rest | Memory.content is stored as plaintext. Implement application-level AES-GCM encryption. Encrypt on write, decrypt on read in MemoryService. Store IV alongside ciphertext. Key from server-side KMS or env var. | server/src/context/memory/index.ts, server/src/lib/crypto.js | P0-05 | 6 | HIGH | TODO | Memory.content in DB is base64-encoded ciphertext. Readable after decrypt via service. Raw DB shows no plaintext.
2 | P3-02 | Encryption | Encrypt message content at rest | Message.parts (JSON containing message text) is plaintext. Apply same AES-GCM encryption pattern as P3-01. Performance critical — measure before/after encryption overhead. | server/src/services/storage-adapter.js, server/src/lib/crypto.js | P3-01 | 6 | HIGH | TODO | Message.parts in DB is ciphertext. Conversation view still shows correct content after decrypt.
3 | P3-03 | Encryption | Encrypt user settings and privacy preferences | User.settings and User.privacyPreferences JSON is plaintext. Encrypt these fields at rest. Audit other Json fields in User model for sensitive content. | server/src/services/ (user service), server/src/lib/crypto.js | P3-01 | 4 | MEDIUM | TODO | User.settings column in DB shows ciphertext. User preferences accessible normally via API.
4 | P3-04 | Data | Implement proper GDPR deletion flow | Account deletion route exists (DELETE /account/me) but GDPR compliance needs verification. Ensure: all user data deleted (conversations, ACUs, memories, context bundles, social connections), deletion confirmation email, 30-day grace period with cancel option. | server/src/routes/account.js, server/src/services/ (new: deletion-service.ts) | P0-09 | 8 | HIGH | TODO | Delete account removes all associated data within 24h. User receives confirmation. Cancel works within 30 days.
5 | P3-05 | Data | Validate data export completeness | Data export is implemented but needs validation. Test exported ZIP/JSON includes: conversations, messages, ACUs, memories, context bundles, social connections, settings. Verify exported data is importable. | server/src/services/portability-service.js, server/src/routes/portability.js | P0-09 | 5 | HIGH | TODO | Export ZIP contains all user data. Import from export restores data correctly. Tested end-to-end.
6 | P3-06 | Data | Add memory TTL / expiration support | Memory model is missing expiresAt field (noted in schema gap analysis). Add migration to add expiresAt. Add background job to prune expired memories. Let users set memory lifetime in settings. | schema.prisma (migration), server/src/context/memory/consolidation.ts | P3-01 | 4 | MEDIUM | TODO | Expired memories not returned by API. Background job prunes them nightly.
7 | P3-07 | Data | Normalize frequently-queried JSON fields | User.settings is a JSON field queried frequently — extract common fields (maxContextTokens, responseStyle, etc.) into dedicated columns. Add migration. Update all query paths. | schema.prisma (migration), server/src/services/*, server/src/routes/* | P0-09 | 8 | MEDIUM | TODO | maxContextTokens queryable directly on User table. JSON field retained for arbitrary extras. No query regressions.
8 | P3-08 | Data | Add missing database indexes | Schema gap analysis identified 3 missing indexes: Memory[userId,type,importance], ACU[authorDid,createdAt], SharingPolicy[ownerId,createdAt]. Create migration to add all three. | schema.prisma (migration) | — | 2 | HIGH | TODO | All 3 indexes exist. EXPLAIN ANALYZE on memory retrieval queries shows index scan, not seq scan.
9 | P3-09 | Data | Add database connection pooling tuning | No visible connection pool configuration. Set Prisma connection pool size (connection_limit). Add PgBouncer or configure Prisma datasource pooling for production load. | server/.env, schema.prisma (datasource block) | — | 3 | MEDIUM | TODO | Connection pool configured. Load test with 100 concurrent users shows no connection pool exhaustion.
10 | P3-10 | Data | Resolve multiple phase schema files | 5 phase schema files (phase1-5) exist alongside main schema.prisma. Consolidate: verify all phase models are in main schema, delete or archive phase files, document the schema evolution. | server/prisma/schema*.prisma | — | 3 | MEDIUM | TODO | Single authoritative schema.prisma. Phase files archived with README. prisma migrate status clean.
11 | P3-11 | Data | Design and document per-user database isolation roadmap | Per-user SQLite is the target architecture but not implemented. Produce a concrete technical design document: migration strategy, dual-write period, rollback plan, timeline. Get team alignment before implementing. | docs/architecture/ (new: user-isolation-design.md) | P3-07, P3-10 | 8 | HIGH | TODO | Design document reviewed. Migration approach agreed. Clear go/no-go criteria defined.
12 | P3-12 | Infra | Add database backup automation | No DB backup strategy documented. Configure pg_dump scheduled backup (daily full, hourly incremental). Store in S3/R2. Test restore procedure. Document RTO/RPO. | deployment scripts, .github/workflows/ or cron config | — | 5 | HIGH | TODO | Daily backup runs automatically. Restore tested successfully from backup. Alert if backup fails.
13 | P3-13 | Audit | Add comprehensive audit logging | Add an audit_log table tracking: who did what, when, on which resource, from which IP. Log: login/logout, data access, share creation, deletion, admin actions. Do not log content. | schema.prisma (AuditLog model), server/src/middleware/ (new: audit.ts) | P0-09 | 6 | HIGH | TODO | All auth events and data mutations logged. Audit log immutable (append-only). Admin can query by user/time.
14 | P3-14 | Privacy | Implement consent and privacy preference enforcement | privacyPreferences field exists on User but enforcement is unclear. Build service that checks privacy prefs before: sharing content, indexing for discovery, including in feed. Block if not consented. | server/src/services/ (new: privacy-enforcement-service.ts) | P3-03 | 6 | HIGH | TODO | User with sharing=false never appears in discovery. Settings change takes effect immediately.
15 | P3-15 | Security | Security penetration test preparation | Prepare for external pen test: document all API routes and auth requirements, create test accounts, identify sensitive data flows. Complete OWASP Top 10 self-assessment checklist. | docs/security/ (new: pentest-prep.md, owasp-assessment.md) | P0-01 through P0-14, P3-13 | 8 | MEDIUM | TODO | OWASP self-assessment complete. All P0 security tasks complete. Pen test ready.
16 | P3-16 | Data | Add content hash verification on ACU read | ACU.contentHash exists (SHA-256). Verify hash on read in GET /acus/:id. Return integrity_failed flag if hash mismatch. Alert on mismatch (possible data tampering). | server/src/routes/acus.js, server/src/lib/crypto.js | P0-02, P1-09 | 3 | MEDIUM | TODO | Manually corrupted ACU content returns integrity_failed: true. Alert fires.

## P4 · Social & Discovery
P4 · Social & Discovery
# | Task ID | Area | Task Title | What To Do | File(s) / Location | Depends On | Effort (hrs) | Priority | Status | Acceptance Criteria
1 | P4-01 | Feed | Implement feed ranking algorithm | Feed route exists but ranking is unclear. Implement weighted score: recency (0.3) + engagement (0.3) + social affinity (0.2) + relevance to context (0.2). A/B test against chronological baseline. | server/src/services/feed-service.js | P1-01, P2-01 | 10 | HIGH | TODO | Feed shows different order than created_at DESC. Engagement signals update ranking within 5 min.
2 | P4-02 | Discovery | Build public ACU discovery page | ForYou.tsx page exists. Connect it to real public ACU data. Show: trending ACUs, recently shared, top by topic. Add pagination. Only show ACUs where sharingPolicy.audience=PUBLIC. | pwa/src/pages/ForYou.tsx, server/src/routes/feed-v2.js | P3-14 | 8 | HIGH | TODO | ForYou page shows real public ACUs. Private ACUs never appear. Loads in <2s with 100 items.
3 | P4-03 | Search | Implement public content full-text search | Search covers conversations but needs to include public ACUs and memories. Add pgvector semantic search + PostgreSQL full-text search (tsvector). Combine results with ranking. | server/src/routes/*, server/src/services/ (new: search-service.ts) | P3-08 | 10 | HIGH | TODO | Search returns both conversations and public ACUs. Semantic and keyword results combined. <500ms at 1k items.
4 | P4-04 | Moderation | Activate moderation enforcement pipeline | Moderation models and routes exist but enforcement is not active. Wire ContentFlag review to: hide content pending review, notify flagged user, auto-hide after N flags, moderator review queue. | server/src/services/moderation-service.js, server/src/routes/moderation.js | P3-14 | 8 | HIGH | TODO | Content with 3 flags auto-hides. Moderator queue shows pending reviews. Resolved flags notify reporter.
5 | P4-05 | Moderation | Implement AI-assisted content moderation | Add automated moderation pass: when content is shared publicly, run LLM classification for SPAM, HATE_SPEECH, DANGEROUS. Flag for human review if confidence >0.8. Do not auto-remove. | server/src/services/moderation-service.js | P4-04 | 8 | HIGH | TODO | Public ACU creation triggers async moderation check. Flagged items queued for human review within 1 minute.
6 | P4-06 | Social | Build user profile pages | Social routes have GET /social/profile/:did but no frontend page. Create PublicProfile.tsx: shows display name, handle, public ACUs, circles, follower/following counts. Respect privacy settings. | pwa/src/pages/ (new: PublicProfile.tsx) | P3-14 | 6 | HIGH | TODO | Visiting /profile/:handle shows public profile. Private info hidden. Follow button functional.
7 | P4-07 | Social | Add follow/friend notification flow | Social routes work but notifications aren't sent. Wire: friend request → notification to recipient, friend accept → notification to requester, follow → notification to followed (if prefs allow). | server/src/routes/social.ts, server/src/services/ (notification-service.ts) | P2-09, P4-06 | 5 | HIGH | TODO | Sending friend request shows notification to recipient. Accept notifies sender. Follows respect notification prefs.
8 | P4-08 | Social | Build circles-based sharing discovery | Users in a circle should see shared ACUs from circle members in their feed. Add 'Circle Feed' tab to Home. Show circle activity sidebar. Distinguish circle vs public content. | pwa/src/pages/Home.tsx, server/src/routes/feed-v2.js | P4-01 | 8 | HIGH | TODO | Circle Feed shows only content from circle members. Correct permissions enforced.
9 | P4-09 | Social | Add topic clustering and tagging to feed | TopicProfile model exists with topics extracted from conversations. Use topics to cluster feed content. Add topic filter to ForYou page. Show 'Because you discussed: {topic}' context. | server/src/services/feed-service.js, pwa/src/pages/ForYou.tsx | P4-02 | 7 | MEDIUM | TODO | Feed items tagged with topic. Topic filter works. Feed explanation shows topic rationale.
10 | P4-10 | Social | Implement share analytics for content creators | ACU has shareCount, quoteCount, viewCount fields. Expose analytics to ACU owner: who viewed (if trackable), how many shares, forks created. Add to Analytics page. | pwa/src/pages/Analytics.tsx, server/src/routes/acus.js | P4-02 | 5 | MEDIUM | TODO | ACU owner sees view/share/fork counts. Analytics page shows engagement trends over time.
11 | P4-11 | Social | Build collaborative notebook (multi-user ACU collections) | ContentStakeholder model exists for collaborative content. Enable shared notebooks: owner invites collaborators, collaborators can add ACUs, all see updates in real-time via Socket.IO. | server/src/routes/context-v2.js, pwa/src/pages/Collections.tsx | P4-08 | 10 | MEDIUM | TODO | User can invite collaborator to notebook. Both can add ACUs. Changes appear without refresh.
12 | P4-12 | Discovery | Add trending topics and entities dashboard | EntityProfile and TopicProfile have engagement metrics. Build a 'Trending' section showing top discussed topics and entities in the last 7 days across public content. | pwa/src/pages/ForYou.tsx, server/src/routes/feed-v2.js | P4-02 | 5 | MEDIUM | TODO | Trending section shows 10 topics and 10 entities updated hourly. Clicking shows related public ACUs.
13 | P4-13 | Social | Add social onboarding (find and follow people) | New users have no social connections. Add step to onboarding: 'Find people to follow' — show suggestions based on topic overlap, invite via email, or search by handle. | pwa/src/pages/ (Onboarding.tsx), server/src/routes/social.ts | P2-01, P4-06 | 6 | MEDIUM | TODO | Onboarding step shows personalized follow suggestions. User can follow 3+ people before finishing.
14 | P4-14 | Social | Implement fork/continuation thread visualization | ACUGraph.tsx exists. Make it the canonical view for fork lineage. Show parent → children tree. Clicking node navigates to that ACU. Show fork count on ACU cards. | pwa/src/components/ACUGraph.tsx, pwa/src/components/ACUViewer.tsx | P2-22 | 6 | MEDIUM | TODO | ACU with forks shows tree graph. Each node is clickable. Fork count shows on ACU card.
15 | P4-15 | Social | Add email notification system | No email service configured. Integrate transactional email (Resend, Postmark, or SES). Send: welcome email, share notification, friend request, weekly digest. Add unsubscribe handling. | server/src/services/ (new: email-service.ts), server/ .env | P4-07 | 8 | MEDIUM | TODO | Welcome email sent on registration. Share notification email delivered. Unsubscribe link works.
16 | P4-16 | Social | Build group channels and posting | Team channels route exists (POST /social/teams/:teamId/channels). Build frontend: channel list sidebar, message composer in channel, message thread view. Real-time via Socket.IO. | pwa/src/ (new channel pages/components), server/src/routes/social.ts | P4-11 | 12 | LOW | TODO | Team members can post in channels. Messages appear in real-time. Message history loads on open.
17 | P4-17 | Discovery | Implement 'For You' feed A/B testing framework | Set up A/B test infrastructure: randomly assign users to feed variants, track engagement metrics per variant, report winner. Start with chronological vs. ranked feed test. | server/src/services/feed-service.js, server/src/services/ (new: ab-test-service.ts) | P4-01 | 8 | LOW | TODO | Users randomly assigned to test variant. Engagement tracked per variant. Dashboard shows results.

## P5 · Infra & Scale
P5 · Scale & Infrastructure
# | Task ID | Area | Task Title | What To Do | File(s) / Location | Depends On | Effort (hrs) | Priority | Status | Acceptance Criteria
1 | P5-01 | DevOps | Build proper CI/CD pipeline | GitHub Actions workflows exist but are basic. Build full pipeline: lint → unit test → integration test → build → deploy to staging → smoke test → deploy to production. Block deploys if any step fails. | .github/workflows/ | P1-15 | 10 | HIGH | TODO | PR triggers full test suite. Merge to main deploys to staging. Manual approval to promote to prod.
2 | P5-02 | DevOps | Add health check endpoints | No health check endpoints documented. Add: GET /health (liveness), GET /ready (readiness including DB and Redis). Used by load balancer and k8s probes. | server/src/server.js (or new health.js route) | — | 2 | HIGH | TODO | GET /health returns 200 always. GET /ready checks DB connectivity. Load balancer uses /ready.
3 | P5-03 | DevOps | Set up monitoring and alerting (Grafana/Datadog) | Pino logging exists. Add: application metrics (response time, error rate, throughput via Prometheus), infrastructure metrics (CPU/memory), custom business metrics (captures/hour, active users). Alert on: error rate >1%, p99 latency >2s, DB connections >80%. | server/src/server.js, deployment config | P5-01, P5-02 | 8 | HIGH | TODO | Grafana dashboard shows real-time metrics. Alerts fire under load test. On-call runbook written.
4 | P5-04 | DevOps | Configure CDN for static assets | No CDN configured. Set up Cloudflare or CloudFront for PWA static assets. Configure Cache-Control headers. Ensure service worker handles CDN URLs. Set up asset fingerprinting. | vercel.json (or CDN config), pwa/vite.config.ts | P5-01 | 4 | HIGH | TODO | PWA assets served from CDN. Cache hit rate >95%. Deploy invalidates CDN cache.
5 | P5-05 | Infra | Production environment configuration | Document and configure all production env vars. Update CORS_ORIGINS to vivim.app. Remove all development defaults. Set DATABASE_SSL_REQUIRED=true. Configure Redis for production. Create production .env template with all required vars. | server/.env.example, all workspace .env files, deployment docs | P0-05, P0-10 | 4 | HIGH | TODO | Production server starts with no dev defaults. SSL required for DB. CORS restricted to vivim.app.
6 | P5-06 | Infra | Load test and performance baseline | Run k6 or Artillery load test simulating 100 concurrent users: 50 browsing feed, 30 sending messages, 20 capturing conversations. Identify bottlenecks. Fix top 3 before beta launch. | tests/load/ (new: load-test.js) | P5-02, P5-03 | 8 | HIGH | TODO | System handles 100 CCU with p99 <2s and <0.1% error rate. Bottlenecks documented and fixed.
7 | P5-07 | Infra | Configure database read replicas | Feed and search are read-heavy. Configure PostgreSQL read replica. Route read queries (feed, search, context retrieval) to replica. Keep writes on primary. | server/.env, schema.prisma (datasource), server/src/services/ | P5-06 | 6 | MEDIUM | TODO | Read replica configured. Feed queries go to replica. Write-heavy operations still go to primary.
8 | P5-08 | P2P | Configure P2P bootstrap peers for network engine | P2P_BOOTSTRAP_PEERS is empty — P2P networking non-operational. Deploy at least 3 bootstrap nodes. Configure LibP2P with their multiaddresses. Verify peer discovery works. | network/ package, server/.env | P5-05 | 8 | MEDIUM | TODO | P2P_BOOTSTRAP_PEERS configured. Admin panel shows connected peers. Yjs sync verified between 2 clients.
9 | P5-09 | Infra | Configure Redis for production caching | Redis is installed (ioredis) but noted as 'Optional (for caching, not actively used)'. Activate Redis for: session caching, rate limiting state, context bundle caching, feed result caching. Set appropriate TTLs. | server/src/server.js, server/src/services/* | P5-05 | 6 | MEDIUM | TODO | Redis cache hit rate >60% for feed requests. Session data in Redis. Context bundles cached with 5-min TTL.
10 | P5-10 | DevOps | Implement blue-green deployment strategy | Deploy new version alongside existing (blue-green). Route traffic gradually. Automated rollback if error rate spikes. Zero-downtime deploys. | .github/workflows/, deployment config | P5-01, P5-03 | 8 | MEDIUM | TODO | Deploy causes zero downtime. Traffic shifted gradually. Rollback completes in <2 minutes.
11 | P5-11 | DevOps | Set up staging environment | No staging environment documented. Configure staging: separate DB (seeded with anonymized data), same infra as prod at smaller scale, deployed on every merge to main. | deployment config, .github/workflows/ | P5-01 | 6 | HIGH | TODO | Staging environment running. QA can test before prod deploy. Staging DB separate from prod.
12 | P5-12 | Infra | Set up log aggregation and search | Pino logs go to file. Aggregate in production: ship to Loki, Datadog, or Papertrail. Enable full-text search of logs. Retention policy: 30 days. Redact sensitive fields from logs. | server/src/server.js (Pino transport config) | P5-03 | 4 | MEDIUM | TODO | All server logs searchable in log platform. Sensitive fields redacted. 30-day retention active.
13 | P5-13 | Infra | Configure email service for production | No email service configured at infrastructure level. Set up SPF, DKIM, DMARC for vivim.app domain. Integrate with transactional email provider (Resend/Postmark). Verify deliverability. | DNS config, server/.env | P4-15 | 4 | MEDIUM | TODO | Emails from notifications@vivim.app delivered to Gmail/Outlook. SPF/DKIM pass. Spam score <3.
14 | P5-14 | DevOps | Create operations runbook | Document: how to deploy, how to rollback, how to scale, how to restore from backup, how to handle incidents, common error codes and remediation, on-call checklist. | docs/ops/ (new: runbook.md) | P5-03, P5-10 | 6 | MEDIUM | TODO | Runbook covers all critical ops scenarios. New engineer can follow runbook to restore from backup.
15 | P5-15 | Infra | Configure auto-scaling | If hosted on cloud (ECS/Fly.io/Railway), configure horizontal auto-scaling based on CPU/request metrics. Define min/max instances. Test scale-up and scale-down behavior. | deployment config | P5-06, P5-09 | 6 | LOW | TODO | Load test triggers scale-out. Traffic served without error during scale event. Scale-in after load drops.
16 | P5-16 | Infra | Set up Sentry for production error tracking | SENTRY_DSN is optional. Configure Sentry for all environments. Set up: release tracking, source maps upload in CI, performance monitoring, user context in error events. Configure alert routing. | server/src/server.js, pwa/src/main.tsx, .github/workflows/ | P5-01 | 4 | HIGH | TODO | Errors appear in Sentry with source-mapped stack traces. Release tags match Git commits. Alerts routed correctly.
17 | P5-17 | DevOps | Implement database migration safety checks | Prisma migrations run in CI. Add: migration dry-run in staging before prod, check for destructive migrations (column drops), require manual approval for breaking migrations. | .github/workflows/, scripts/ (new: migration-safety-check.sh) | P5-11 | 4 | MEDIUM | TODO | Destructive migration blocked from auto-deploy. Dry-run runs in staging first. Approval required.
18 | P5-18 | Infra | Performance optimization: API response caching | Add HTTP caching headers to appropriate endpoints: GET /api/v2/feed (1 min), GET /ai-settings/providers (1 hour), GET /conversations/stats (5 min). Use Redis cache-aside pattern. | server/src/routes/*, server/src/server.js | P5-09 | 5 | LOW | TODO | Cache headers present on specified endpoints. Redis shows cache hits. Feed endpoint latency <100ms with warm cache.

## 🔗 Dependency Map
VIVIM — Critical Dependency Chains
These chains must complete in order. No task can start until its prerequisites are done.
CHAIN 1: Auth Foundation → Everything Else
| Step | Task ID | Title | Target Day | Unlocks
| 1 | P0-01 | Remove SKIP_AUTH flag | Day 1
| 2 | P0-02 | Auth all ACU routes | Day 1
| 3 | P0-03 | Auth all context routes | Day 1
| 4 | P0-04 | Assign ownerId on capture | Day 2
| 5 | P0-09 | Ownership checks in all services | Day 3
| 6 | P1-01 | Integration test ownerId flows | Day 4
CHAIN 2: Capture Reliability → Growth
| Step | Task ID | Title | Target Day | Unlocks
| 1 | P1-02 | Circuit breaker for extractors | Day 5
| 2 | P1-04 | Test all 9 extractors live | Day 6-7
| 3 | P1-13 | Configure Playwright browser pool | Day 7
| 4 | P1-15 | Capture test suite in CI | Day 8
| 5 | P4-01 | Feed ranking algorithm | Day 15+
| 6 | P4-02 | Public ACU discovery | Day 17+
CHAIN 3: Security → Trust → Beta
| Step | Task ID | Title | Target Day | Unlocks
| 1 | P0-05 | Rotate all secrets | Day 1
| 2 | P0-06 | JWT expiry + refresh | Day 2
| 3 | P0-07 | CSRF protection | Day 3
| 4 | P3-01 | Encrypt memories at rest | Day 10
| 5 | P3-02 | Encrypt messages at rest | Day 11
| 6 | P3-13 | Audit logging | Day 13
| 7 | P3-15 | Pen test prep | Day 20+
CHAIN 4: UX → Retention
| Step | Task ID | Title | Target Day | Unlocks
| 1 | P2-01 | Guided onboarding flow | Day 8
| 2 | P2-02 | Demo conversation for new users | Day 9
| 3 | P2-03 | PWA installability | Day 8
| 4 | P2-04 | Mobile layout fixes | Day 9-11
| 5 | P2-09 | In-app notifications | Day 12
| 6 | P4-06 | User profile pages | Day 16
CHAIN 5: Infrastructure → Launch
| Step | Task ID | Title | Target Day | Unlocks
| 1 | P5-01 | Full CI/CD pipeline | Day 14
| 2 | P5-02 | Health check endpoints | Day 8
| 3 | P5-11 | Staging environment | Day 14
| 4 | P5-03 | Monitoring + alerting | Day 15
| 5 | P5-06 | Load test | Day 18
| 6 | P5-16 | Sentry production | Day 14

## ✅ Launch Checklist
VIVIM — Production Beta Launch Checklist
SECURITY
✓ | Task | Requirement | Phase | Priority
☐ | P0-01 complete | No SKIP_AUTH_FOR_DEVELOPMENT in codebase | P0 | BLOCKING
☐ | P0-02 complete | All ACU routes require auth | P0 | BLOCKING
☐ | P0-03 complete | All context routes require auth | P0 | BLOCKING
☐ | P0-04 complete | ownerId assigned on all captures | P0 | BLOCKING
☐ | P0-05 complete | No real secrets in any committed file | P0 | BLOCKING
☐ | P0-06 complete | JWT tokens expire in 15 minutes | P0 | HIGH
☐ | P0-07 complete | CSRF protection active | P0 | HIGH
☐ | P0-08 complete | Rate limiting on all endpoints | P0 | HIGH
☐ | P0-10 complete | CORS restricted to vivim.app | P0 | HIGH
☐ | P3-01 complete | Memories encrypted at rest | P3 | HIGH
☐ | P3-02 complete | Messages encrypted at rest | P3 | HIGH
CAPTURE
✓ | Task | Requirement | Phase | Priority
☐ | P1-01 complete | ownerId integration test passes | P1 | BLOCKING
☐ | P1-02 complete | Circuit breaker active for all providers | P1 | HIGH
☐ | P1-04 complete | All 9 extractors tested and passing | P1 | HIGH
☐ | P1-13 complete | Playwright browser pool configured in prod | P1 | HIGH
☐ | P1-15 complete | Capture test suite in CI | P1 | HIGH
☐ | P1-17 complete | Sentry tracking capture errors | P1 | HIGH
UX & PRODUCT
✓ | Task | Requirement | Phase | Priority
☐ | P2-01 complete | Onboarding flow built and tested | P2 | HIGH
☐ | P2-03 complete | PWA installable on iOS + Android | P2 | HIGH
☐ | P2-04 complete | Mobile layout passes 390px test | P2 | HIGH
☐ | P2-06 complete | All pages have error states | P2 | HIGH
☐ | P2-09 complete | In-app notifications working | P2 | HIGH
☐ | P2-15 complete | Lighthouse scores ≥85/90/90/90 | P2 | MEDIUM
DATA & TRUST
✓ | Task | Requirement | Phase | Priority
☐ | P3-04 complete | GDPR deletion flow verified | P3 | HIGH
☐ | P3-05 complete | Data export tested end-to-end | P3 | HIGH
☐ | P3-08 complete | Missing DB indexes added | P3 | HIGH
☐ | P3-12 complete | Automated DB backups running | P3 | HIGH
☐ | P3-13 complete | Audit logging active | P3 | HIGH
INFRASTRUCTURE
✓ | Task | Requirement | Phase | Priority
☐ | P5-01 complete | CI/CD pipeline: all stages passing | P5 | HIGH
☐ | P5-02 complete | Health check endpoints live | P5 | HIGH
☐ | P5-03 complete | Monitoring + alerting configured | P5 | HIGH
☐ | P5-05 complete | Production env vars all correct | P5 | BLOCKING
☐ | P5-06 complete | Load test: 100 CCU with <2s p99 | P5 | HIGH
☐ | P5-11 complete | Staging environment running | P5 | HIGH
☐ | P5-16 complete | Sentry source maps in production | P5 | HIGH
MODERATION (required for public launch)
✓ | Task | Requirement | Phase | Priority
☐ | P4-04 complete | Moderation enforcement pipeline active | P4 | HIGH
☐ | P4-05 complete | AI-assisted moderation running | P4 | HIGH
☐ | P3-14 complete | Privacy preference enforcement active | P3 | HIGH